## HTML5 Validation Task List
Id | Area | Task | Estimate | Priority | Assigned To | Status | Due Date | java (Mac OSX) | php (Win7) | ruby (Linux) | Release
1 | User Experience | HTML5 SDK source and package (zip) obtained from Github using readme |  | 1 | [6 empty] | 1
2 |  | Use package to create Mac OSX and Java Server (jetty) |  | 1 |  |  |  |  | NA | NA | 1
3 |  | Use package to create Win7 and PHP server (apache, etc) |  | 1 |  |  |  | NA |  | NA | 1
4 |  | Use package to create Linux and Ruby server (sinatra) |  | 1 |  |  |  | NA | NA |  | 1
5 |  | Manual Spot test HTML5 sample apps against SDK on Webkit |  | 1 | [6 empty] | 1
6 |  | Document review (regress previous issues) |  | 1 | [6 empty] | 1
7 | Design | Code review - No Sencha Touch lib in package |  | 1 | [6 empty] | 1
8 |  | Code review - No Sencha Direct dependency on server side |  | 1 | [6 empty] | 1
9 |  | Code review - AT&T codekit lib leveraged by server code |  | 1 | [6 empty] | 1
10 |  | Code review - other items per user stories |  | 1 | [6 empty] | 1
11 | Functional | Automated Test Harness - runs on all suppported servers |  | 1 | [6 empty] | 1
12 | Automated | Automated Test Harness - produces reliable and readable logs |  | 1 | [6 empty] | 1
13 |  | Automated Test Harness - docs describe how to setup, run, create logs |  | 1 | [6 empty] | 1
14 |  | Automated Test Harness - docs describe architecture |  | 1 | [6 empty] | 1
15 |  | Automated Build - compiles SDK when changes introduced |  | 1 |  |  |  |  | NA |  | 1
16 |  | Automated Build - docs describe architecture |  | 1 | [6 empty] | 1
17 | OAuth | OAuth - OAuth Consent (Speech SMS MMS) |  | 1 | [6 empty] | 1
18 |  | OAuth - OAuth Client Credentials (Speech SMS MMS) |  | 1 | [6 empty] | 1
19 | Speech | QUnit Speech API test - Speech To Text |  | 2 | [6 empty] | 1
20 |  | QUnit Speech API test - Text To Speech |  | 2 | [6 empty] | 1
21 |  | QUnit Speech API test - Speech To Text Custom |  | 2 | [6 empty] | 1
22 |  | Selenium Speech API test - Speech To Text |  | 2 | [6 empty] | 1
23 |  | Selenium Speech API test - Text To Speech |  | 2 | [6 empty] | 1
24 |  | Selenium Speech API test - Speech To Text Custom |  | 2 | [6 empty] | 1
25 |  | Speech API - Speech Sample App |  | 2 | [6 empty] | 1
26 | SMS | QUnit SMS API test - Send SMS |  | 2 | [6 empty] | 2
27 |  | QUnit SMS API test - Get SMS Status |  | 2 | [6 empty] | 2
28 |  | QUnit SMS API test - Receive SMS |  | 2 | [6 empty] | 2
29 |  | QUnit SMS API test - Get SMS |  | 2 | [6 empty] | 2
30 |  | Selenium SMS API test - Send SMS |  | 2 | [6 empty] | 2
31 |  | Selenium SMS API test - Get SMS Status |  | 2 | [6 empty] | 2
32 |  | Selenium SMS API test - Receive SMS |  | 2 | [6 empty] | 2
33 |  | Selenium SMS API test - Get SMS |  | 2 | [6 empty] | 2
34 |  | SMS API - SMS Sample App |  | 2 | [6 empty] | 2
35 | MMS | QUnit MMS API test - Get MMS |  | 2 | [6 empty] | 2
36 |  | QUnit MMS API test - Get MMS Status |  | 2 | [6 empty] | 2
37 |  | QUnit MMS API test - Receive MMS |  | 2 | [6 empty] | 2
38 |  | QUnit MMS API test - Receive MMS Status |  | 2 | [6 empty] | 2
39 |  | Selenium MMS API test - Get MMS |  | 2 | [6 empty] | 2
40 |  | Selenium MMS API test - Get MMS Status |  | 2 | [6 empty] | 2
41 |  | Selenium MMS API test - Receive MMS |  | 2 | [6 empty] | 2
42 |  | Selenium MMS API test - Receive MMS Status |  | 2 | [6 empty] | 2
43 |  | MMS API - MMS Sample App |  | 2 | [6 empty] | 2
44 | OAuth | OAuth - OAuth Advice of Charge (Payment) |  | 1 | [6 empty] | 1
45 | Payment | QUnit Payment API test - New Transaction |  | 3 | [6 empty] | 2
46 |  | QUnit Payment API test - Get Transaction Status |  | 3 | [6 empty] | 2
47 |  | QUnit Payment API test - Transaction Redund |  | 3 | [6 empty] | 2
48 |  | QUnit Payment API test - Transaction Notification |  | 3 | [6 empty] | 2
49 |  | QUnit Payment API test - Create Subscription |  | 3 | [6 empty] | 2
50 |  | QUnit Payment API test - Get Subscription Status |  | 3 | [6 empty] | 2
51 |  | QUnit Payment API test - Get Subscription Details |  | 3 | [6 empty] | 2
52 |  | QUnit Payment API test - Subscription Refund |  | 3 | [6 empty] | 2
53 |  | QUnit Payment API test - Subscription Notification |  | 3 | [6 empty] | 2
54 |  | Selenium Payment API test - New Transaction |  | 3 | [6 empty] | 2
55 |  | Selenium Payment API test - Get Transaction Status |  | 3 | [6 empty] | 2
56 |  | Selenium Payment API test - Transaction Redund |  | 3 | [6 empty] | 2
57 |  | Selenium Payment API test - Transaction Notification |  | 3 | [6 empty] | 2
58 |  | Selenium Payment API test - Create Subscription |  | 3 | [6 empty] | 2
59 |  | Selenium Payment API test - Get Subscription Status |  | 3 | [6 empty] | 2
60 |  | Selenium Payment API test - Get Subscription Details |  | 3 | [6 empty] | 2
61 |  | Selenium Payment API test - Subscription Refund |  | 3 | [6 empty] | 2
62 |  | Selenium Payment API test - Subscription Notification |  | 3 | [6 empty] | 2
63 |  | Payment API - Payment Sample App |  | 3 | [6 empty] | 2
64 | Ads | QUnit Ads API test - Get Advertisement |  | 1 | [6 empty] | 2
65 |  | Ads API - Ads Sample App |  | 1 | [6 empty] | 2
66 | In-App Msging | QUnit In-App Messaging API test - Create Msg Index |  | 1 | [6 empty] | 2
67 |  | QUnit In-App Messaging API test - Delete Msg |  | 1 | [6 empty] | 2
68 |  | QUnit In-App Messaging API test - Delete Msgs |  | 1 | [6 empty] | 2
69 |  | QUnit In-App Messaging API test - Get Msgs |  | 1 | [6 empty] | 2
70 |  | QUnit In-App Messaging API test - Get Msg Content |  | 1 | [6 empty] | 2
71 |  | QUnit In-App Messaging API test - Get Msg Index Info |  | 1 | [6 empty] | 2
72 |  | QUnit In-App Messaging API test - Get Msg List |  | 1 | [6 empty] | 2
73 |  | QUnit In-App Messaging API test - Get Msg Delta |  | 1 | [6 empty] | 2
74 |  | QUnit In-App Messaging API test - Get Notification Connection Details |  | 1 | [6 empty] | 2
75 |  | QUnit In-App Messaging API test - Send Msg |  | 1 | [6 empty] | 2
76 |  | QUnit In-App Messaging API test - Update Msg |  | 1 | [6 empty] | 2
77 |  | QUnit In-App Messaging API test - Update Msgs |  | 1 | [6 empty] | 2
78 |  | Selenium In-App Messaging API test - Create Msg Index |  | 1 | [6 empty] | 2
79 |  | Selenium In-App Messaging API test - Delete Msg |  | 1 | [6 empty] | 2
80 |  | Selenium In-App Messaging API test - Delete Msgs |  | 1 | [6 empty] | 2
81 |  | Selenium In-App Messaging API test - Get Msgs |  | 1 | [6 empty] | 2
82 |  | Selenium In-App Messaging API test - Get Msg Content |  | 1 | [6 empty] | 2
83 |  | Selenium In-App Messaging API test - Get Msg Index Info |  | 1 | [6 empty] | 2
84 |  | Selenium In-App Messaging API test - Get Msg List |  | 1 | [6 empty] | 2
85 |  | Selenium In-App Messaging API test - Get Msg Delta |  | 1 | [6 empty] | 2
86 |  | Selenium In-App Messaging API test - Get Notification Connection Details |  | 1 | [6 empty] | 2
87 |  | Selenium In-App Messaging API test - Send Msg |  | 1 | [6 empty] | 2
88 |  | Selenium In-App Messaging API test - Update Msg |  | 1 | [6 empty] | 2
89 |  | Selenium In-App Messaging API test - Update Msgs |  | 1 | [6 empty] | 2
90 |  | In-App Messaging API - In-App Msg Sample App |  | 1 | [6 empty] | 2
91 |  | Vendor whitebox test criteria passed |  | 1 | [6 empty] | 2