## HTML5 Validation Task List
Id | Area | Task | Estimate | Priority | Assigned To | Status | Due Date | Java (Mac OSX) | PHP (Win7) | Ruby (Linux) | Release
1 | User Experience | HTML5 SDK source and package (zip) obtained from Github using readme | M | 1 | [6 empty] | 1
2 |  | Use package to create Mac OSX and Java Server (jetty) | S | 1 |  |  |  |  | NA | NA | 1
3 |  | Use package to create Win7 and PHP server (apache, etc) | S | 1 |  |  |  | NA |  | NA | 1
4 |  | Use package to create Linux and Ruby server (sinatra) | S | 1 |  |  |  | NA | NA |  | 1
5 |  | Manual Spot test HTML5 sample apps against SDK on Webkit | L | 1 | [6 empty] | 1
6 |  | Document review (regress previous issues) | L | 1 | [6 empty] | 1
7 | Design | Code review - No Sencha Touch lib in package | XS | 1 | [6 empty] | 1
8 |  | Code review - No Sencha Direct dependency on server side | S | 1 | [6 empty] | 1
9 |  | Code review - AT&T codekit lib leveraged by server code | M | 1 | [6 empty] | 1
10 |  | Code review - other items per user stories | XL | 1 | [6 empty] | 1
11 | Functional | Automated Test Harness - runs on all suppported servers | M | 1 | [6 empty] | 1
12 | Automated | Automated Test Harness - produces reliable and readable logs | L | 1 | [6 empty] | 1
13 |  | Automated Test Harness - docs describe how to setup, run, create logs | M | 1 | [6 empty] | 1
14 |  | Automated Test Harness - docs describe architecture | S | 1 | [6 empty] | 1
15 |  | Automated Build - compiles SDK when changes introduced | S | 1 |  |  |  |  | NA |  | 1
16 |  | Automated Build - docs describe architecture | S | 1 | [6 empty] | 1
17 | OAuth | OAuth - OAuth Consent (IAM, DC) | M | 1 | [6 empty] | 1
18 |  | OAuth - OAuth Client Credentials (Speech, SMS, MMS, ADS) | S | 1 | [6 empty] | 1
19 | Speech | Speech API test - Speech To Text | S | 2 | [6 empty] | 1
20 |  | Speech API test - Text To Speech | S | 2 | [6 empty] | 1
21 |  | Speech API test - Speech To Text Custom | S | 2 | [6 empty] | 1
22 |  | Speech API - Speech Sample Apps | M | 2 | [6 empty] | 1
23 | SMS | SMS API test - Send SMS | M | 2 | [6 empty] | 2
24 |  | SMS API test - Get SMS Status | M | 2 | [6 empty] | 2
25 |  | SMS API test - Receive SMS | L | 2 | [6 empty] | 2
26 |  | SMS API test - Get SMS | L | 2 | [6 empty] | 2
27 |  | SMS API - SMS Sample Apps | L | 2 | [6 empty] | 2
28 | MMS | MMS API test - Get MMS | M | 2 | [6 empty] | 2
29 |  | MMS API test - Get MMS Status | S | 2 | [6 empty] | 2
30 |  | MMS API test - Receive MMS | L | 2 | [6 empty] | 2
31 |  | MMS API test - Receive MMS Status | L | 2 | [6 empty] | 2
32 |  | MMS API - MMS Sample Apps | L | 2 | [6 empty] | 2
33 | OAuth | OAuth - OAuth Advice of Charge (Payment) | M | 1 | [6 empty] | 1
34 | Payment | Payment API test - New Transaction | S | 3 | [6 empty] | 2
35 |  | Payment API test - Get Transaction Status | S | 3 | [6 empty] | 2
36 |  | Payment API test - Transaction Refund | S | 3 | [6 empty] | 2
37 |  | Payment API test - Transaction Notification | L | 3 | [6 empty] | 2
38 |  | Payment API test - Create Subscription | S | 3 | [6 empty] | 2
39 |  | Payment API test - Get Subscription Status | S | 3 | [6 empty] | 2
40 |  | Payment API test - Get Subscription Details | S | 3 | [6 empty] | 2
41 |  | Payment API test - Subscription Refund | M | 3 | [6 empty] | 2
42 |  | Payment API test - Subscription Notification | L | 3 | [6 empty] | 2
43 |  | Payment API test -Notary | S | 3 | [6 empty] | 2
44 |  | Payment API - Payment Sample Apps | M | 3 | [6 empty] | 2
45 | Ads | Get Advertisement | S | 1 | [6 empty] | 2
46 |  | Ads API - Ads Sample App | S | 1 | [6 empty] | 2
47 | In-App Msging | In-App Messaging API test - Create Msg Index | S | 1 | [6 empty] | 2
48 |  | In-App Messaging API test - Delete Msg | S | 1 | [6 empty] | 2
49 |  | In-App Messaging API test - Delete Msgs | S | 1 | [6 empty] | 2
50 |  | In-App Messaging API test - Get Msgs | M | 1 | [6 empty] | 2
51 |  | In-App Messaging API test - Get Msg Content | M | 1 | [6 empty] | 2
52 |  | In-App Messaging API test - Get Msg Index Info | S | 1 | [6 empty] | 2
53 |  | In-App Messaging API test - Get Msg List | S | 1 | [6 empty] | 2
54 |  | In-App Messaging API test - Get Msg Delta | S | 1 | [6 empty] | 2
55 |  | In-App Messaging API test - Get Notification Connection Details | XS | 1 | [6 empty] | 2
56 |  | In-App Messaging API test - Send Msg | M | 1 | [6 empty] | 2
57 |  | In-App Messaging API test - Update Msg | S | 1 | [6 empty] | 2
58 |  | In-App Messaging API test - Update Msgs | M | 1 | [6 empty] | 2
59 |  | In-App Messaging API - In-App Msg Sample App | XL | 1 | [6 empty] | 2
60 |  | Vendor whitebox test criteria passed | XXL | 1 | [6 empty] | 2
61 | Qunit | Qunit - Speech Tests | S | 1 | [6 empty] | 2
62 |  | Qunit - Custom Speech Tests | S | 1 | [6 empty] | 2
63 |  | Qunit - Text to Speech Tests | S | 1 | [6 empty] | 2
64 |  | Qunit SMS Tests | S | 1 | [6 empty] | 2
65 |  | Qunit MMS Tests | S | 1 | [6 empty] | 2
66 |  | Qunit IAM Tests | S | 1 | [6 empty] | 2
67 |  | Qunit Ads Test | S | 1 | [6 empty] | 2
68 |  | Qunit Payment Transaction | S | 1 | [6 empty] | 2
69 |  | Qunit Payment Subscription | S | 1 | [6 empty] | 2
70 | Selenium | Selenium Test Suite | M | 1 | [6 empty] | 2